# Appendix X: U15 Féile Planning & Matchday Guide

## 1. Féile Preparation Timeline

☐ Host fundraiser(s)

☐ Order Féile gear (10-12 weeks before)

☐ Submit Féile panel(s)

☐ Participate in grading games

☐ Confirm hosting arrangements

☐ Coordinate Féile communications

☐ Finalise matchday logistics

## 2. Administration & Compliance (12-14 Weeks Before)

☐ Confirm Lead Mentor and coaching team roles

☐ Ensure at least one qualified First Aider is available

☐ Review Féile regulations with all mentors

☐ Nominate official club photographer

☐ Confirm player eligibility

☐ Verify all players are registered members

☐ Update emergency contacts

☐ Confirm medical conditions/allergies

☐ Confirm social media permissions

☐ Finalise fundraising plans

☐ Confirm available budget

☐ Obtain supplier quotations

☐ Confirm player sizing

☐ Place gear order

☐ Organise gear presentation day

☐ Take team and individual photographs

## 3. Féile Planning (6-8 Weeks Before)

☐ Finalise Féile panel

☐ Review regulations regarding players playing up

☐ Establish substitution strategy

☐ Identify leadership group/captains

☐ Agree team goals and objectives

## 4. Parent Communication

☐ Hold Féile parent meeting

☐ Explain competition format

☐ Explain fundraising requirements

☐ Explain travel arrangements

☐ Confirm attendance expectations

☐ Outline sideline behaviour expectations

☐ Organise volunteers

☐ Establish communication channel for Féile weekend

## 5. Logistics & Operations

☐ Confirm fixtures

☐ Confirm venues

☐ Confirm throw-in times

☐ Share fixture details with parents

☐ Confirm referee arrangements

☐ Prepare travel itinerary

☐ Organise transport

☐ Build in contingency time

☐ Match jerseys

☐ Spare jerseys

☐ Match balls/sliotars

☐ Bibs

☐ Cones

☐ Water carriers

☐ First aid kit

☐ Ice packs

☐ Coaches bibs

☐ Team sheets

☐ Tent/Pavilion if required

## 6. Player Welfare & Safety

☐ Confirm first aid cover

☐ Review concussion procedures

☐ Review emergency procedures

☐ Identify nearest AED

☐ Confirm supervision ratios

☐ Ensure no player is left unsupervised

☐ Confirm hydration plan

☐ Encourage appropriate nutrition

☐ Monitor training load in lead-up

## 6A. Safeguarding & Photography

☐ Confirm official photographer

☐ Confirm social media permissions

☐ Remind mentors that coaching staff should not take photographs during games

☐ Ensure all photographs comply with club safeguarding policy

☐ Share photographs through approved club channels only

## 7. Final Week Preparation

☐ Reduce overall volume

☐ Maintain intensity

☐ Practice restarts and set plays

☐ Practice penalties if relevant

☐ Reinforce team principles

☐ Focus on confidence and enjoyment

☐ Confirm player availability

☐ Confirm jersey numbering

☐ Confirm player roles

☐ Review opposition if known

☐ Finalise matchday timetable

## 8. Féile Matchday Checklist

☐ Team sheets completed

☐ First aid kit packed

☐ Ice packs packed

☐ Match balls packed

☐ Jerseys packed

☐ Water available

☐ Emergency contacts accessible

☐ Arrive early

☐ Set up team base area

☐ Set up warm-up area

☐ Meet referee

☐ Confirm dressing room arrangements

☐ Complete structured warm-up

☐ Positive sideline behaviour

☐ Manage substitutions

☐ Monitor injuries and fatigue

☐ Hydration

☐ Nutrition/snacks

☐ Recovery walk/stretch

☐ Review key learnings

☐ Keep players positive and relaxed

☐ Thank referees

☐ Thank opposition

☐ Account for all players

☐ Return equipment

☐ Record injuries

☐ Update parents

☐ Hold post-Féile team gathering

## 9. Post-Féile Review

☐ Hold mentor review meeting

☐ Review player development outcomes

☐ Gather player feedback

☐ Gather parent feedback

☐ Recognise volunteers

☐ Celebrate player effort and achievement

☐ Update player development notes

☐ Document lessons learned

☐ Share learnings with Juvenile Committee

## Notes

Féile is intended to be a memorable player experience as much as a competition. Planning should focus equally on player enjoyment, participation, welfare, team bonding and club representation, regardless of results achieved on the field.